## Proposed Product Backlog
Category | User Stories (Epics)
User | As a user, I want to be able to select start game or exit game so that I can navigate the main menu
As a user, I want to be able to understand the goal of the game so that I know how to play
As a user, I want to be able to see what wave I am currently on so that I know my progress
As a user, I want to be able to see my current score so that I know how well I am doing
As a user, if I win or lose, I want to be able to see my final score so that I can compare previous hi-scores
As a user, if I win or lose, I want to be able to restart or close the game so that I can continue or leave
Friendly object | As a friendly object, I want to be able to move with AD/Vim keybindings so that I can move
As a friendly object, I want to be able to shoot a missile using the spacebar so I can eliminate enemies
As a friendly object, I want to explode on contact with an enemy object so that I know when I die
Enemy object | As an enemy object, I want to spawn at the start of a new wave so that the user has a goal
As an enemy object, I want to descend across the playfield, increasing in speed with each wave so that there is a lose condition
As an enemy object, I want to explode on contact with a friendly object so that I can be eliminated from the playing field
As an enemy object, I want to move left/right across the playfield, increasing in speed with each wave so that the game is more difficult
Program | As a program, when all enemies are off playing field, new wave begins so that the game can continue properly
As a program, when wave 5 is complete, congratulations screen is shown so that the user knows they won
As a program, if the user dies, game over screen is shown so that the user knows they died
Each user story must have all of three clauses: As a … I want … so that

## Sprint 1
Sprint Backlog: Sprint 1
Category | EPICs (User Stories) | ID | Child User Stories | Status | Notes
User | As a user, I want to have a menu screen so that I can know what I am supposed to do in the game. | 1 | As a user, I want to be able to select start game or exit game so that I can navigate the main menu | completed | new EPIC
|  | 2 | As a user, I want to be able to understand the goal of the game so that I know how to play | completed | new EPIC
| As a user, I want to know my current game status on the playing field so that I can track how well I am doing | 3 | As a user, I want to be able to see what wave I am currently on so that I know my progress |  | new EPIC
|  | 4 | As a user, I want to be able to see my current score so that I know how well I am doing |  | new EPIC
Friendly Object | As a friendly object, I want to interact with the user and enemy objects so that I am a dynamic object on the playing field | 5 | As a friendly object, I want to be able to move with AD/Vim keybindings so that I can move |  | new EPIC
|  | 6 | As a friendly object, I want to be able to shoot a missile using the spacebar so I can eliminate enemies |  | new EPIC
Each child user story must have all of 3 clauses too: As a … I want to … so that
You are allowed to introduce a new EPIC that is not in the proposed Product Backlog. In "Notes" column, remark it as a new EPIC. However, do not edit the original Product Backlog.

## Sprint 1 Acceptance
Child User Story ID | Acceptance Criteria | Result | Note
1 | The shooter moves to the right by 10 pixels with the right arrow key press | pass
| The shooter moves to the left by 10 pixels with the left arrow key press | pass
| The shooter moves upwards by 10 pixels with the up arrow key press | pass
| The shooter moves downwards by 10 pixels with the down arrow key press | pass
| As left key is pressed 20 times, the shooter crosses from right edge to left edge of screen | fail | incorrect screen size may be used
| As right key is pressed 20 times, the shooter crosses horizontally from right edge to left edge of the screen | fail | incorrect screen size may be used
| For each of 4 arrow keys, the shooter moves continuously as the key is kept pressing | pass
2 | At the right edge, the shooter does not move to the right arrow key press | pass
| At the left edge, the shooter does not move to the left arrow key press | pass
| At the top edge, the shooter does not move to the up arrow key press | pass
| At the bottom edge, the shooter does not move to the down arrow key press | pass
| At the four corners of the game scene, the shooter stays inside the scene after pressing arrow keys | pass
3 | The missile launches always from the shoot as shoot changes its location | pass
| The missile launches and travels to the mouse press location. | pass
| Several mouse press locations with various angles from the shooter must be verified | pass
4 | The missile radius increases at the mouse press location | fail | the mouse press location is occasionally not detected.
| Multiple and fast mouse presses need to be verified | fail
5 | The missile radius stops increasing at the radius of 35 pixels. | pass
| The missile disappears from the game scene once explosion radius reaches 35 pixels | pass
More than 1 acceptance criteria per child user story is strictly required. If you cannot find multiple acceptance criteria for a child user story, you need to redesign the child user story. It is too small. Acceptance criterion must NOT be mere repetition of child user story. It must contain more info for proper testing.

## Finalized Product Backlog
Completed Child User Stories Based on the Submitted Program. Closely related child user stories may be merged into one user story.
Category | Child User Stories | Status | Notes